The method statement for construction work

PURPOSE

To specify the requirements of civil construction including excavation, filling, and allied activities complying with the contract document, specification, and scope of work and approved drawings/documents. It also includes earthworks associated with trenches for pipelines or service ducts.

# SCOPE

This Method Statement applies to all the civil works - Excavation including ground preparation, setting out, backfilling, soil compaction, concreting, waterproofing, masonry, plastering, joinery - related to the construction of building as per project requirements, referring with approved Civil and MEP drawing.

# ROLES & RESPONSIBILITY

The primary responsibility of carrying out all the activities mentioned in this procedure rests with the site- in-charge unless mentioned otherwise.

Project Leader:

Overall execution and administration of the project as per contract requirements, specifications and the for preparation and updating of PQP. Directly control the Site Engineers and Supervisors.

Site Engineer:

Assess manpower, equipment or other resources required to ensure timely completion of the project. Monitor availability of all materials as per schedule. Inform the Project Leader for any non-availability of materials to take proper action. Carry out receiving inspection in coordination with the QA/QC Engineer. Ensure  that the drawings and documents are up to date and the latest drawing is available and is being utilized in the project site works. Filled-up the check-sheet and submit the necessary IR to the QA/QC function when the work is ready for inspection.

QA/QC Engineer: Responsible for the monitoring and implementing of quality related matters and ensure the works are being executed with the approved Project Quality Plan and requirements of the Contract Documents, sections 1 part 8 of QCS 2010, approved method statement and ITPs.

Safety Officer: Responsible for monitoring and implementation of safety related matters such as work permits, First Aid, PPE, approval of diversions, follow the safety and traffic regulations by all the workmen during the construction, according to the approved project HSE plan. First Aid boxes are readily available with HSE officer and other two numbers at site personnel’s vehicles for site requirements.

Supervisor/Foreman:

Plan and obtain required manpower and resources in coordination with the Site Engineer. Carry out all activities as per the planned schedule to achieve target dates. Coordinate with respective disciplines of work and liaise with the site engineer for day to day activities. Inform Discipline Engineer regarding site inspections when it is ready. Ensure pre task briefing is to be conducted prior to start of work at each session.

Charge hand:

Works shall be executed as per direction of Supervisors/Foremen for all activities as per the planned schedule to achieve target. Coordinate with respective

disciplines of work and liaise with the Supervisors/Foremen for day to  day  activities. Ensure pre task briefing is conducted prior to start of work at each session.

# REFERENCE DOCUMENTS

Contract Document & Bill Of Quantities.

Civil structural and architectural drawing issued for construction. QCS 2010 and Project Specifications.

# ABBREVIATIONS

Main Contractor

Consultant	To be filled

Client or Customer	To be filled

Site-in-charge	For the purpose of this procedure, the term Site-In-charge

Shall mean Project/Site Engineer.

# INSPECTION & TESTING

Site inspection/approval shall be in accordance with the approved Inspection and Test Plan for all activities in addition to the Quality Control Procedure and Project Quality Plan for the Project.

All the required site test shall be conducted as per the Section-21,

# WORK PERMITS

All necessary work permits shall be obtained prior to the commencement of any activity at site and shall remain valid throughout the entire duration of the operation.

Safety Barriers and Site sign boards will be installed prior to the work commencement.

# HEALTH, SAFETY AND ENVIRONMENTAL PROCEDURES

Requirements of Health, Safety and Environmental for the project shall be in accordance with approved Project HSE Plan, the contract document and Part-15 & 19, section.

Before commencing of any work, the required and applicable work permits shall be checked and ensure all requirements of WP are compiled and they are valid until completion of the activity and as per approved HSE plan.

All personnel accessing their site will wear the mandatory PPE. All workmen and staff shall wear the mandatory and job specific Personnel Protective Equipment's. Pre-task briefing shall be conducted on every day before starting the work. Experienced and HSE inducted workmen shall be deployed for the work. All personnel shall be cautioned while working near any live lines such as power cable, water lines, drainage lines, telecom etc.

Prior to commencement of work all workers shall be given pre-task briefing. Hazards identified for the activity shall be disseminated during pre-task briefing, especially for underground services, slip & trip, improper access, excavation tools handling, no access or

aggress, vehicle collision, heat exhaustion, which shall be identified and documented separately by permit to work system as per approved HSE plan.

First aid stations complete with all first aid equipment and trained first aiders shall be maintained for the initial care.

Safety and security procedures shall be implemented as a minimal, warning signs and lights, barricades, railing and other safeguards shall be provided as required by the nature and location of the work.

The environmental risk assessment and environmental management plans have been reviewed for the work activities proposed in the method statement and found to be suitable and adequate.

Electrical waste will be segregated at source and transported to dedicated segregated waste storage area and not be allowed to accumulate on site in undesignated areas. Concrete waste will be removed from work areas at regular intervals to designated areas.

Construction waste will be disposed as per local laws & client guidelines by licensed carrier to a licensed facility.

# QUALITY ASSURANCE & CONTROL

The Quality Assurance and Control for the above mentioned activities shall be exercised and recorded in accordance with the contract documents, applicable section 1, and part 8 of QCS 2010 for Quality Assurance and the approved Project Quality Plan for the project.

The quality assurance shall be ensured for workmanship, equipments and materials conformance to the applicable standards and requirements at every stage of the construction. This shall be monitored by quality control personnel or designated substitute on the site during the production / operation.

Quality assurance requirements shall also be imposed upon sub-contractors, suppliers, manufacturers and any other parties associated and involved in the project. Non-conforming materials shall be notified in writing to correct or remove the defective materials from the work site.

All inspections and tests shall be conducted in accordance with written test procedures as detailed in the Project Quality Plan and Inspection and Test Plan approved by the GEIC Engineer.

Applicable documents with latest version such as Inspection & Test Plan, Method Statements shall be readily available and used by inspection and test personnel at the time of inspection as referring documents.

# MATERIALS

Approval shall be obtained for all the materials with reference to Client’s preferred vendor list, prior to	commencement of activities.

Material Inspection Request (MIR) will be submitted to client upon material arrival to warehouse.

All materials must be stored properly as per the manufacturer’s recommendations and QCS. The Material shelf life will be monitored as per Manufacturer’s data sheets

# MANPOWER

Site Engineer Supervisor HSE Inspector

QA/QC Inspector Carpenters

Steel Fixers Masons Helpers Painters Operators

Drivers & Technicians

# EQUIPMENT & TOOLS

The following equipments and tools shall be used for the various activities. Excavators

Shovels

JCB

Self-Loaders Bobcat

Tipper Trucks / Trailers Water Tankers Rollers/Compactors Transit Mixers Concrete pump Vibrators

Dewatering pump Mobile crane Angle Grinders Cutters

Drilling Machines Wheel Barrows Bagger mixer Hand tools

# WORK PROCEDURE FOR CONSTRUCTION OF OTHER CIVIL JOBS

  - Initial Survey & Site Checking

Upon receipt of Job Instruction / Drawing form Consultant Engineer, an initial site visit to be made along with the consultant representative to confirm the site and demarcations.

Proper Safety Fencing and site sign boards will be installed prior to the construction

# Back filling and Compaction.

Back filling material shall be as per QCS 2002-Section-12-Part 3-Clauses 3.2.2, 3.2.3.

Back filling shall be done in layers of not more than 250mm loose thickness as per QCS 2002-Section-12-Part 3.5 and each layer thoroughly watered and rammed to ensure Minimum Dry Density of 95%.Testing of compaction will be performed as directed by the engineer.

Earth work under substructure shall be provided with anti-termite treatment for the approval of the Engineer.

# Construction of RCC Foundation, Columns, Grade Beam, Roof Beam and Slab

The bottom of excavation shall be compacted and offered for inspection and testing by the consultant Engineer. Over excavation should be provided with SRC 20 concrete to the required Level.

On approval of above activity, 75mm thick blinding concrete shall be laid to the required levels and size, supplied from approved ready mix plant.

After completing the excavation works, activities for Foundation to be carried out first, followed with columns up to slab height completed later plinth and inside room work to be started.

# Reinforcing steel

Engineer’s approval will be obtained for reinforcement before using in permanent works.

All reinforcement will be stored on racks inside the stores. Different types & sizes will be kept separately. All reinforcement will be kept to protect from damage, free from dirt, loose mill scale, rust scale paint, oil, or other foreign substances.

As per the specifications & drawing, the bar bending schedules & bar lists, cutting schedules for each individual structure will be prepared by the contractor and will obtained the approval from the engineer.

Manual cutter or mechanical cutter will be used for cutting of bars & bending machine will be used for bending of bars.

All reinforcement will be cleaned by a wire brush or any other means before placing.

All reinforcement placed should comply with the drawings. Lap length will be taken in to account according to the project specification when binding reinforcement bars.

Form work

All formwork will be made by using plywood sheets, timber or by metal.

Supports and scaffolding will be G I pipes, Arco props, sawn timber or round timber. All surfaces of formwork will be finished smooth and mortar tight.

The dimensions & position of formwork will be carefully checked after erection.

Oil or grease will be used to avoid adhesion of mortar and to achieve a smooth surface.

Before placing concrete all dirt, wood chips, hardened concrete or mortar and all other foreign matter will be removed from the forms.

Before fixing of form work, detailed drawing will be submitted to the engineer for approval. Well qualified foremans will be appointed for fixing on formworks & reinforcement work.

# Placing of concrete

The method for placing of concrete will be worked out to prevent segregation of the material & Engineer’s approval will be taken before concreting begins.

Before placing concrete all formwork therein will be cleaned of all extraneous material and dust and made free of any standing water.

In continuing concrete, fresh concrete will be placed before the already placed concrete is less than 20 minutes.

Concrete of specified grade will be placed & compacted in horizontal layers normally not exceeding 300mm in depth.

Concrete will not be dropped from a height greater than 1.5m to prevent segregation. Concrete will be free of all rock pockets, honey combs & voids.

Complete Records showing the details of placing concrete in each part of the work will be maintained and will be available for inspection at the site.

# Compacting / vibrating of concrete

Mechanical vibrators will be used for compaction. For this stand by units will available in the site during the period of compacting. All operators handling vibrators will be trained in their operation properly.

# Curing

Continuous curing will be carried out in a moist atmosphere for a minimum period of 10 days and for a further period required by engineer.

Concrete area will be kept covered with hessian clothes or Polyethylene sheets which will  be kept moist throughout the curing period.

# Construction joints.

The surface of the hardened concrete will be cleaned and made free from laitance, and will also have an exposed aggregate finish.

The fresh concrete will be placed and compacted so that it bonds properly to the prepared surface of the previously laid concrete.

Laitance on the surface will be completely removed from the concrete in order to achieve a good bond with fresh concrete.

Between one and two hours after placing concrete, water will be sprayed gently and laitance will be removed with two brushes, one with soft and other with hard bristles.

After finishing this operation, just the tips of the aggregate should be showing.

If the laitance has hardened, a wire brush will be used to remove it. Clean water will be rinsed to get rid of the dust.

Water stops in construction joints will be installed & approval for this will be taken from the engineer.

# Checking water content & slump test

Frequent slump test will be carried out in accordance with BS 1881 on samples of concrete taken immediately before placing to determine the consistency of concrete.

All the test reports will be maintained in the site office & will be available for the inspection whenever required.

# Testing of concrete

All necessary arrangements for the sampling & testing of fresh & harden concrete in accordance with the BS 1881 will be taken.

Crushing test will be carried out on concrete cubes formed in 150mm molds. One set of cubes (2 cubes crushed in 7 days & other in 28days) will be done to maintain the quality of work.

Particular care will be taken to ensure that the test cubes are stored under uniform conditions in the site & during any transit between site & laboratory.

# Waterproofing

Ensure that all preceding activities or activities completed which cannot be accessed after waterproofing works are inspected, released and approved.

Obtain MEP clearance and clearance from other specialist trades which may not be accessible after waterproofing, prior to commencing waterproofing works.

Rectify non-conforming conditions prior to commencing the waterproofing works.

# Surface Preparation

All surfaces to receive waterproofing to be clean, dry and free from dirt, dust, oil and grease.

Wall Protrusions that likely to punch through the waterproofing films to be removed either by using a chipping hammer or grinder.

Prepare and level the concrete surfaces for waterproofing either by chipping, hacking or scraping the surface.

Repair the excessive pinholes, and similar imperfections (if any) to eliminate uneven surface.

Barricade the working area as to be a non-trafficking passage.

Raise an inspection request for surface preparation (RFI) prior to the waterproofing work commences.

# Installation of Accessories and marking of Waterproofing Levels

Immediately after the inspection use Viscose Elastic type adhesive tape at week joints and sharp edges.

Marking of waterproofing application levels can be commenced at this stage.

Levels should be true, square and in plumb at locations as indicated on the approved shop drawings/IFC drawings.

Use suitable fasteners when required.

Install waterproof level pads also to serve as guides in controlling the final thickness of the waterproof and the finished plane of the waterproofed surface, relative to the accessories installed.

# Application and Protection

Ensure all other trades in the said location are put on hold during the waterproof application so to protect and avoid any damage to the waterproofing layers.

Apply first coat using a manual brush application uniformly at a workable consistency.

Floor application should continue to the vertical wall face up to a minimum of 150mm as per the project specifications.

Ensure all surfaces to receive waterproofing fluid Application firmly to achieve good adhesion and to be in one continuous operation.

Subsequent coats of waterproof may be commenced immediately after setting of the previous coat approximately 3 to 5 hours and as per the manufactures recommendations.

Second coat should be applied at a right angle to the first coat. Finish coats to be fairly true to the plane with a homogenous finish

Approved Bitumen Impregnated Protection Boards should be provided for protection with sufficient lapping as per the manufactures recommendation.

Footings shall be protected by 4mm thick waterproofing membrane sheets laid on concrete surfaces primed with bituthene primer.

Laid sheets shall be protected from Damage by using bituminous protection boards or 40mm SRC screed concrete as horizontal protection.

Vertical faces shall be protected against damage from backfilling by using Servipak6 or equivalent protection boards.

All application shall be according to manufactures instructions only.

Approval shall be obtained from the Engineer prior to commence the backfilling works.

# Masonry

Block works shall be done as per approved drawings and shall comply with QCS.

All block works executed below ground level built with S.R C cement and shall built in

S.R.C mortar. Normal weight Hollow Blocks having a minimum compressive strength of 7.0 N/mm2 shall be used.

Samples of each type of masonry unit and accessory shall be submitted to consultant for approval.

Marking up of exact location of block walls and openings as per approved shop drawings shall be done before commencing the work.

Block marked areas shall be cleaned and wet before to start with the activity. Mortar mix shall comply with project specifications and QCS.

One course of block only will be executed for testing and approval by the consultant.

Walls shall be kept level at all times and carried up in a uniform manner. No part being raised more than 1500mm above any adjacent unbuilt course.

Angles & Reveals shall be kept true, square and plumb all the time.

Horizontal joints shall be leveled all the time and vertical joints in alternate courses shall be plumb and line.

Opening frames shall be set and maintained square, plumb, true and furnished with anchors.

Install reinforced concrete block lintels or GI steel lintels over openings as per approved shop drawing or cast in places as per specification.

Top of block partitions and sides will be supported by using galvanized steel anchors/ties as per approved shop drawings and material submittals.

Concrete block walls and partitions shall be reinforced horizontally each second course, last top course, second and third course above lintels and below sills of opening with the required over lap.

After completing of each section of the walls, cleaning shall be done to the down surfaces and curing will start immediately.

Final inspection shall be carried out for the entire work for approval of the engineer.

# Plastering

Prepare surfaces for the smooth or non-absorbent solid surfaces that do not have the suction capability to receive a solid plaster bases by chipping, wire brushing or sand blasting, as appropriate.

Install beads at their locations plumbed and squared. And it will be best achieved by using galvanized nails or small quantities of mortar and as per manufacturer’s recommendations.

Install the corner, control joints and movement beads at locations indicated in the drawings and manufacturer’s instructions.

Prepare plaster in a mechanical mixer, using sufficient water to produce a workable consistency and uniform color shall be used to mix a batch containing one bag of Portland cement, 5 parts aggregate, aerating plasticizer as per manufacturer’s recommendation for use over Concrete Unit Masonry.

Spray water on the wall surface and throw the spatter dash mix (scratch coat) by using a spatter dash manual machine in a way to form a rough layer 3-5mm thick without any attempt to level or smooth it. The rough surface shall be kept damp with fine water spray or by covering with polyethylene sheet until it sets down.

Apply plaster/render coat after the scratch coat had hardened. Initially, a thin coat is troweled on the scratch coat to ensure a thorough bonding at the surface.

The remainder of the render coat is then built up using wooden float to receive textured finish until the required thickness met.

Apply final thin coat plastering using steel trowel on the interior surface to match with the Architect’s sample as specified.

The coating thickness shall not deviate more than +/- (6.4mm in 3m) from the trueness of  the plastered finish, as measured with straight edge placed on the surface.

The newly applied external coatings shall be cured and protected against frost, heat, and rain for the first 48 hours using canvass, cloth or sheet, hung clear at the plaster surface. Moist curing by applying a fine fog spray of water, generally twice daily in the morning and evening.

# HEALTH & SAFETY

Refer to the site safety policy for general safety controls. One of the main aspects of this procedure is Safety and Health Control. This is to control occurrence of injuries as well as damage to equipment and properties during the entire construction period.

Tool Box meetings shall be conducted on every day before the start of the work. Experienced workmen only shall be deployed for the work.

All personnel shall be cautioned while working near the pipes/ cables.

Hazard identification shall be done during toolbox meetings especially for heat

In order to ensure a safe working environment during the entire construction period, the following safety measures will be implemented.

# Machineryand Equipment:

Prior to use any machinery/equipment at site, it shall be inspected and certified by qualified person.

Periodic Preventive Maintenance shall be made on all equipment and machineries.

All operators and driver are to be equipped with valid driver’s/operator’s license or permit from concerned government agency.

Only authorized drivers or operators will be allowed to operate machineries or equipment. Only authorized signalman shall be assigned together with the operator or driver.

All lifting equipment as well as its accessories such as sling wire, nylon sling, shackles, chain blocks, crane hook and latch shall be inspected periodically.

# Personal Protective Equipment:

PPE shall be issued to all workers such as safety shoes, hard hat, working gloves, ear plugs, safety goggles and safety belt and or safety harness for workers who will be assigned in elevated places.

Wearing of the basic PPE shall be enforced fully.

# EMERGENCY CONTACTS

| Sl. No. | Position | Name | Contact No. |
| --- | --- | --- | --- |
| 1 | Project Manager |  |  |
| 2 | Site Engineer |  |  |
| 3 | Safety officer |  |  |